## Start Here
DSI Test Status — Simple Monitoring View
Prepared 8 Sep 2026 ¦ Proposed reconciliation for Roger, Charlee and Emman review. Source workbooks are unchanged.
Topic | Plain-language meaning
What this file is for | One place to see what is truly tested, what “PASS” means, and the next step. It prevents the team from repeating work.
Use this first | Read the Dashboard, then the Test Monitor. Charlee should work only on items labelled “Next test”.
Important rule | A local or review-stage PASS is not the same as a full end-to-end PASS.
Current source of test results | DSI_AI_Employee_Test_Case_Document (1).xlsx — newest test register, modified 8 Sep 2026.
Current project source | DSI_AI_Employee_System_Master_PM_3 — project tasks, owners and dependencies, modified 5 Sep 2026.
Status labels | PASS — Local; PASS — Review-stage; PASS — Live connector; PASS — End-to-end; HOLD; BLOCKED.
What is not changed | This file does not update the official test workbook or PM workbook. Owners must approve any official status change.

## Dashboard
DSI Test Status — Dashboard
Quick view for monitoring. Counts are based on the proposed matrix in the Test Monitor tab.
Measure | Count / status | What it means
Controls/tests listed |  | Items included in this reconciliation
Accepted at local/review stage |  | Passed in a bounded test; not full live E2E
Still needs evidence |  | Do not mark complete
TC-10 status |  | 30-row test materials ready; actual run still needed
Production sends/writes | 0 | No live send or production CRM/CQL write authorized by these results
Next focus | TC-10 execution + confirm live connector evidence for CQL/Smartlead | One bounded next step, not a full rerun

## Test Monitor
DSI Test Monitor — Plain Language
Use this tab to decide what Charlee should test next. “Accepted result” means accepted only at the stated evidence level.
ID | Area | Current status | Evidence level | What is already accepted | What is still missing | Next test / action | Owner
TC-07 | Apollo filters | PASS — Local | Local | Mock test handles unknown filters and stops on unclear scope. | Live Apollo behavior not proven. | Independent review and link the evidence. | Charlee / Emman
TC-09 | Apollo → Clay data handling | PASS — Local | Local | 24 local tests for synthetic data handling. | Live connector E2E not proven. | Do not repeat local suite; only test live E2E if requested. | Charlee
TC-10 | Fabricated/unsupported contacts | HOLD | Fixture only | 30 fake rows and expected answers were reviewed. | The 30 rows have not been run and independently reviewed. | Run all 30; record actual vs expected; attach evidence; independent review. | Charlee → Emman
TC-11–14 | CQL safety | PASS — Local | Local / review-stage | Synthetic suppression, duplicate, disqualified, failure and read-only checks recorded. | Live read path/adapter evidence must be confirmed separately. | Confirm live adapter/read-path evidence; otherwise keep local label. | Alvin / Charlee
TC-15–16 | Smartlead no-send guard | PASS — Local | Local / staging | Draft-only and 14/14 blocking checks recorded. | Current connector readiness is separate. | Confirm current connector check; do not repeat guard suite. | Charlee
TC-21–24 | Safety behavior | PASS — Local | Local | Duplicate, failure, usage-limit and STOP checks recorded. | Not full live workflow proof. | Use as prerequisite; retest only if implementation changed. | Charlee / Joey
TC-25 | Unsupported claim | PASS — Review-stage | Review-stage | System returned No Data/unverified; no side effects. | Not production behavior. | Keep bounded; no repeat unless implementation changes. | Roger / Emman
TC-26 | Evidence records | PASS — Local | Local | Required audit fields are defined/checked. | Full cross-system ledger still needs reconciliation. | Roger confirms links and ledger references. | Roger
TC-27 / CC-16 | Validation ladder | PASS — Review-stage | Review-stage | 10 → 25 → rerun → 50 record ladder passed; side effects 0. | Does not prove production readiness or E2E. | Choose one next live/non-production segment. | Roger / Charlee
CC-04–11 | Governance controls | PASS — Local | Local | Architecture, permissions, routing and request rules recorded. | Some row-link/live enforcement checks remain. | Reconcile links; do not recreate completed local tests. | Roger / Charlee / Ali / Joey
CC-13 | CQL change control | PASS — Local | Local | 6/6 synthetic CQL safety checks recorded. | Live adapter/read-path evidence may still be missing. | Confirm whether live evidence exists; otherwise label local. | Alvin / Charlee
CC-14 | Smartlead change control | PASS — Local | Local / staging | Draft-only and 14/14 no-send guard recorded. | Live connector readiness not proven by this alone. | Confirm current /campaigns connector evidence. | Charlee
CC-15 | Golden/negative tests | PASS — Local | Local | 8/8 focused + 25/25 dependent local tests and independent review. | Not E2E proof. | Do not repeat; use as prerequisite. | Roger / Joey
CC-16 | Review-stage ladder | PASS — Review-stage | Review-stage | All four bounded stages and closure recorded. | Not production launch approval. | Define next bounded workflow segment. | Roger / Charlee

## Evidence Detail
Evidence Detail
Technical references are kept here so the main monitor stays readable.
ID | Evidence noted | Boundary / caveat | Source
TC-10 | Synthetic fixture review approved 4 Sep 2026; 30 IDs, including fabrication traps. | No execution PASS; no production use. | Sept. 8 test workbook + fixture package
CC-13 | 6/6 synthetic CQL validations recorded. | Local/non-production; live read-path must be separately verified. | Sept. 8 test workbook
CC-14 | 14/14 no-send guard tests; campaign draft-only. | No live send; connector readiness separate. | Sept. 8 test workbook
CC-15 | Focused 8/8, dependent 25/25; independent review noted. | Local synthetic/non-production. | Sept. 8 test workbook
CC-16 | Stage 2 Clay d749de64; Stage 3 rerun 44cbb069; Stage 4 manifest 012dccba; Stage 4 Clay a368476b. | Review-stage; all side effects recorded 0; no production authorization. | Sept. 8 test workbook
CC-10 repo | Repository records 6/6 local validator cases; package Ready for Review, not Done. | Local fixture only; human technical review/PM acceptance blank in repo package. | dsi-ai-employee-system-v2, CC-10-freeze

## Next Actions
Next Actions — Keep It Simple
Only one owner and one acceptance condition per action. Update this tab after review; do not silently change official statuses.
Priority | Action | Owner | Done when | Status | Notes
1 | Run TC-10 30-row fixture | Charlee | All 30 rows have actual result, expected result, disposition and evidence link. | OPEN | Independent reviewer/counter-signature required.
2 | Review TC-10 execution | Emman | Reviewer confirms results and any mismatches. | WAITING | Do not call PASS before review.
3 | Confirm CQL live evidence | Alvin / Charlee | Adapter/read path, mapping and fail-closed evidence are linked—or clearly marked not available. | OPEN | Do not repeat synthetic checks.
4 | Confirm Smartlead connector evidence | Charlee | Current connector check is attached; no-send guard remains separate. | OPEN | No launch, send or enrollment.
5 | Approve reconciliation labels | Roger / Charlee / Emman | Reviewers agree on source hierarchy and layer labels. | WAITING | This file is proposed, not an official update.
6 | Run next bounded workflow segment | Charlee | One segment completes with input, output, stop rule and evidence. | BLOCKED BY 1–5 | Start at first unverified dependency.